| This report and any technical reports (no longer than 4 pages) or final deliverables (e.g., studies, reports, etc.) need to be uploaded to Smartsheet. These reports and deliverables are viewable by USB staff only. For Progress Reports: You are also required to provide a Progress Summary. This item will be shared publicly, so it should contain non-proprietary, non-confidential information. For Final Reports: You are also required to provide a Final Summary and Benefits to Soybean Farmers. These items will be shared publicly, so they should contain non-proprietary, non-confidential information. The boxes to enter the summary/benefits information and to upload reports to Smartsheet can be accessed by clicking the “Open Request” button located in your Smartsheet email notification. |  |
| --- | --- |
| ## Project Title: | Spray Application of Double Stranded RNA for Simultaneous Management of Multiple Soybean Fungal and Insect Diseases |
| ## Organization: | Louisiana State University Agricultural Center |
| ## Project Lead Name: | Zhi-Yuan Chen |
| ## Reporting Period: Please select the appropriate reporting period for this report. | ☒ December ☐ March ☐ June ☐ September ☐ Final |
| ## The information included in this detailed report should reflect quantifiable results that can be used to evaluate and measure project success. ## If Progress Report – What key activities were undertaken and what were the key accomplishments during this reporting period? List each key deliverable from the proposal and describe progress made (or not made) toward achieving it, including metrics were appropriate. ## If Final Report – What were the key accomplishments during the life of the project? List each deliverable from the proposal and describe progress made (or not made) toward achieving it, including metrics where appropriate. |  |
| The objectives of this project for the current year include: 1) Continue the effort to fine-tune the conditions to increase the efficacy of dsRNA in disease suppression; 2) Examine the potential of mixing different dsRNA to enhance their effectiveness in reducing disease symptoms under greenhouse conditions; and 3) Perform small scale field studies to determine the effectiveness of these dsRNAs in simultaneous management of Cercospora leaf blight, frogeye leaf spot and purple seed stains through foliar applications. This reporting period mainly focuses on objective 3: conducting field studies to evaluate the effectiveness of different dsRNA in reducing cercospora diseases, such as CLB and FLS (objective 3). Two separate studies were conducted in the field: one was to assess the effect of 3 different dsRNAs and 2 different adjuvants in suppressing frogeye leaf spot disease. Due to the frequent afternoon rains in mid to late July when the dsRNAs were applied, no clear suppression in disease severity was observed in the plants treated with dsRNAs. The other study, which was started two weeks later, was to evaluate whether nanoparticles can enhance the effect of dsRNA and extend the protection of foliar applied dsRNA. Soybean leaf samples were collected 10, 20 and 30 days after the initial treatment. We finished collecting the samples at the end of last quarter. This quarter has been focusing scanning the leaf samples for quantification of disease severity, and for grinding the leaf samples, extracting genomic DNA, quantifying fungal growth, and comparing for differences among the treatments. We just finished analyzing the data of leaves collected at 10 days post initial treatment. A clear reduction in disease severity and fungal growth under field conditions was observed when the plants were sprayed with our gene specific dsRNA. The addition of either adjuvant or nanomaterial to the formulation can further enhance its effectiveness in disease reduction and fungal growth suppression. We have also conducted other growth chamber and greenhouse studies to identify additional gene targets for suppression via foliar dsRNA application. The following genes can be effectively targeted by dsRNAs application, such as CYTB1 and S12 for controlling soybean rust, and CTB1 and CB3 for controlling frogeye leaf spot. For details, please see the technical report. We are currently working analyzing the leaf samples collected at 20 and 30 days after the initial dsRNA treatment and will provide you an update in next quarter report. |  |