| This report and any technical reports (no longer than 4 pages) or final deliverables (e.g., studies, reports, etc.) need to be uploaded to Smartsheet. These reports and deliverables are viewable by USB staff only. For Progress Reports: You are also required to provide a Progress Summary. This item will be shared publicly, so it should contain non-proprietary, non-confidential information. For Final Reports: You are also required to provide a Final Summary and Benefits to Soybean Farmers. These items will be shared publicly, so they should contain non-proprietary, non-confidential information. The boxes to enter the summary/benefits information and to upload reports to Smartsheet can be accessed by clicking the “Open Request” button located in your Smartsheet email notification. |  |
| --- | --- |
| ## Project Title: | Expanding Potential Market Demand for and Access to Whole Soy Foods through Nutrition Education |
| ## Organization: | University of Arkansas Division of Agriculture and University of Missouri |
| ## Project Lead Name: | Leigh Ann Bullington |
| ## Reporting Period: Please select the appropriate reporting period for this report. | ☒ December ☐ March ☐ June ☐ September ☐ Final |
| ## The information included in this detailed report should reflect quantifiable results that can be used to evaluate and measure project success. ## If Progress Report – What key activities were undertaken and what were the key accomplishments during this reporting period? List each key deliverable from the proposal and describe progress made (or not made) toward achieving it, including metrics were appropriate. ## If Final Report – What were the key accomplishments during the life of the project? List each deliverable from the proposal and describe progress made (or not made) toward achieving it, including metrics where appropriate. |  |
| Objective 1. Increase awareness about soy milk and whole / minimally processed (w/mp) soy foods in school and early childcare centers through a multipronged intervention involving taste tests and work with educational influencers. Arkansas – Soy nutrition education was presented to 59 County Extension Agent – Family and Consumer Sciences CEA-FCS during their Best Care in-service. The in-service provided train the trainer information using the newly printed “Soybeans on Your Plate: Nutrition and Health Benefits” Fact Sheet, the newly developed Soybeans fact sheet and lesson plan from our Arkansas Food series and our newly developed tabletop display. CEA-FCS will then use the information they received to train local childcare providers across the state this spring. CEA-FCS will also provide a tasting opportunity for the day care providers to enhance the desire to include minimally processed soy foods in the daycare menus. Missouri – No activities to report this quarter Objective 2. Improve access to soy milk and (w/mp) soy foods in school and early childcare centers. Arkansas – No activities to report this quarter. Missouri – No activities to report this quarter. Objective 3. Increase the availability of soy foods in local food systems while exploring viable connections between producers and consumers Arkansas – No activities to report this quarter. Missouri – During the Wurdack Extension & Research Farm Field Day, a soy presentation and soybean trail mix food demonstration was presented to 500 FFA students. At the Southwest Center Research Farm Field Day, 350 FFA students participated in a soy awareness presentation and a soybean trail mix food demonstration. The promotion of incorporation of soy foods in the diets of those who suffer from Alpha-Gal was presented during the University of Missouri Extension & Engagement Week for 74 participants. Objective 4. Increase appeal and demand for soy foods through education that includes local demonstrations for consumers and producers. Arkansas – Five of the Arkansas Co Grant PIs provided samples of a trail-mix made with roasted soybeans and roasted edamame, at a booth at the Arkansas Farm Bureau State Meeting in their trade show area. They also made available copies of the newly printed “Soybeans on Your Plate: Nutrition and Health Benefits” Fact Sheet and utilized the newly developed tabletop display. Approximately 150 participated in the trade show. Missouri – The addition of soy food demonstrations have been included in recent pilot programming focused on Alpha-Gal Outreach. In Fulton, Missouri, sixteen participants tasted Edamame Slaw Turkey Sliders in a pita. This demonstration will be replicated for another fifteen participants in Linn, MO. |  |