| Please use this form to clearly and concisely report on project progress. The information included should reflect quantifiable results that can be used to evaluate and measure project success. Comments should be limited to the designated boxes. Technical reports, no longer than 4 pages, may be attached to this summary report. |  |
| --- | --- |
| ## Project Title: | Screening elite soybean lines for drought tolerance and developing high-throughput drought screening methodologies for the Mid-South |
| ## Organization: | University of Arkansas |
| ## Principal Investigator Name: | Caio Canella Vieira |
| ## Report Period: | April 1 – June 15, 2026 |
| ## Project Status: Ongoing (Year 1) |  |
| Objective 1: Develop and then validate high-throughput screening tools using drone-based and physiological data to identify traits associated with drought tolerance. These tools will facilitate selection processes and improve the efficiency of breeding programs focused on developing drought-tolerant cultivars. In 2026, 20 entries, including 12 Arkansas MG4E breeding lines and 8 commercial checks, are being evaluated in the Mid-South Drought Trial (MSDT) under irrigated and rainfed conditions using a randomized complete block design with two replications. The trial was planted in Arkansas, Louisiana, and Texas around early May. Drone-based phenotyping is being used to collect physiological data at multiple growth stages throughout the season. Data from the early-vegetative (V3) and late-vegetative (V6) stages have been collected under both irrigation treatments, while data from the reproductive stages will be collected later this summer. These measurements will be used to quantify physiological responses to water limitation and support the identification and selection of drought-tolerant breeding lines. Objective 2: Screen elite soybean lines for drought tolerance across multiple Mid-South environments under irrigated and rainfed conditions in Arkansas, Louisiana, and Texas. This screening will help identify genotypes with high yield and stable performance, and minimal yield loss under drought conditions. In 2026, 12 MG4 breeding lines developed by the University of Arkansas Soybean Breeding Program (9 conventional and 3 Enlist E3) and 8 commercial checks were entered into multi-location testing across Arkansas, Louisiana, and Texas (Table 1). Entries are being evaluated for yield, canopy wilting, and other agronomic traits under irrigated and rainfed conditions. Results from yield testing and drone-based phenotyping will be used to identify high-yielding lines with stable performance across environments and improved drought tolerance based on reduced yield loss under water-limited conditions. Table 1. The information of testing lines and commercial checks in 2026. Name; Pedigree; MG; Type. R23PR-00043E; R15-2422*4 x CTV-DNR-1006; 4E; E3. R23KB-05543; R16-259 x V14-1219; 4E; Convention. R23KB-06518; R18C-11860 x R18-14445; 4E; Convention. R23KB-06553; R18C-11860 x R18-14445; 4E; Convention. R19C-1035; S09-13635 x R11-328:38; 4E; Convention. R21C-02295; S13-2743C x R16-259; 4E; Convention. R22KB-00989; LD12-459 x R16-253; 4E; Convention. R22KB-07724; R16-253 x S13-2743C; 4E; Convention. R22KB-17158; PI568254 x Illini4218N; 4E; Convention. R23PR-00045E; R15-2422*4 x CTV-DNR-1006; 4E; E3. R23KB-06163; R16-259 x V14-1219; 4E; Convention. R23KB-13478E; R16-259*4 x CTV-DNR-1006; 4E; E3. AG39XF3; Check; 3L; XF. AG40XF5; Check; 4E; XF. P42A84E; Check; 4E; E3. AG44XF4; Check; 4E; XF. LD15-3818; Check; 4E; Convention. Becks 4337XF; Check; 4E; XF. P45Z21E; Check; 4M; E3. P47Z15BE; Check; 4L; E3. |